## Action Plan_Instructions
Q4T (Quality for Teens) Action Plan
This action plan provides your improvement team with space to track your selected improvement goals, change strategies, action items, and measurement goals from Q4T (Quality for Teens): A Quality Improvement Package for Adolescent Sexual and Reproductive Health Care. From the list below, select which improvement goal(s) your team will work on to improve and then go to the associated tab to develop your action plan. The last tab in this action plan provides guidance on who to include in your improvement team, space to track team members, and key questions that will help you develop your timeline. This action plan is intended to be a living document that improvement team members can update in real time. Think about where best to save this document so that all team members are able to access it as needed.
Improvement Goal | Worksheet Number and Title | Selected Improvement Goal?
Recommended Screening for Sexual Activity and Sexual Risk Assessment Conducted | 1. Recommended Screening
Behavioral Counseling Related to Sexual Health Conducted | 2. Behavioral Counseling
Recommended Chlamydia and Gonorrhea Screening & Follow Up Conducted | 3. CT GC Screening & Follow Up
Patient-centered Contraceptive Counseling Provided | 4. Contraceptive Counseling
Same-Day Access to Full Range of Contraceptive Methods Provided | 5. Same-Day Access
Welcoming and Accessible Environment Established | 6. Welcoming and Accessible
Confidentiality Protected | 7. Confidentiality
Trauma-informed Approach Integrated into Care | 8. Trauma-Informed

## 1. Recommended Screening
Improvement Goal: Recommended Screening For Sexual Activity And Sexual Risk Assessment Conducted
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Implement a clinic workflow to conduct a risk assessment using a tool that includes sexual risk | Service delivery | Screening Tool Comparison Chart | Identify which screening tool to use during visits; train care team in using identified tool; implement workflow to incorporate screening | Clinical champion | 2/5/2023 | Percent of unduplicated adolescent patients who had a sexual history taken | Monthly | 30% increase in percent of unduplicated clients who had a sexual history taken in 3 months
#N/A
#N/A
#N/A

## 2. Behavioral Counseling
Improvement Goal: Behavioral Counseling Related To Sexual Health Conducted
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Equip parents to have conversations with their adolescents that reinforce behavioral counseling messages | Engaging adolescent patients and families | Talking with your Teens about Sex (CDC) | Print fact sheet; provide fact sheet at each visit to parents | Nurse Manager | 2/5/2023 | Percent of parents who receive fact sheet at visit | Monthly | 70% of all parents attending visit with adolescent receive handout in next 3 months
#N/A
#N/A
#N/A
v
v

## 3. CT GC Screening & Follow Up
Improvement Goal: Recommended Chlamydia And Gonorrhea Screening & Follow Up Conducted
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Implement a clinic workflow to conduct recommended chlamydia and gonorrhea screening | Service delivery | Chlamydia Screening Starter Guide | Develop workflow to ensure that all recommended patients are screened; build in reminder systems to EHR; pull/analyze screening rates on a monthly basis | Health informatics specialist | 2/5/2023 | Percent of unduplicated sexually active adolescent patients who are screened for chlamydia and gonorrhea | Monthly | 50% increase in unduplicated sexually active adolescent patients who are screened for CT/GC in 6 months
#N/A
#N/A
#N/A

## 4. Contraceptive Couns.
Improvement Goal: Patient-Centered Contraceptive Counseling Provided
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Train the care team in shared-decision making and communication skills to deliver patient-centered contraceptive counseling | Equipping teams | CAP E-Learning Program | Schedule time for all care team members to complete CAP E-Learning Program | Implementation team will identify time for care team members to complete program | 2/5/2023 | Percent of care team trained to provide patient-centered contraceptive counseling | Monthly | 100% of care team members trained in 12 months
#N/A
#N/A
#N/A

## 5. Same-Day Access
Improvement Goal: Same-Day Access To Full Range Of Contraceptive Methods Provided
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Train and mentor care team members in LARC insertion, management, and removal | Equipping teams | Clinical Mentor Toolkit | Lead clinician will organize LARC training, schedule training date/clinicians to attend; ensure supplies are in stock | Lead clinician & nurse manager | 2/5/2023 | Number of clinicians trained in LARC insertion, removal, and management | Monthly | 15 more providers trained in 6 months
Implement a clinic workflow to ensure same-day contraceptive access is available every day of clinical services | Service Delivery
#N/A
#N/A

## 6. Welcoming and Accessible
Improvement Goal: Welcoming And Accesible Environment Established
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Train staff to provide respectful, inclusive, youth-friendly care | Equipping teams | Spark Trainings | Schedule time for all care team members to complete Spark trainings | Implementation team will identify time for care team members to complete program | 2/5/2023 | Percent of care team trained to provide respectful, inclusive care | Monthly | 100% of care team members trained in 12 months
#N/A
#N/A
#N/A

## 7. Confidentiality
Improvement Goal: Confidentiality Protected
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Implement a clinic workflow to provide time alone at every patient visit | Service delivery | Adolescent Risk Screening Starter Guide | Develop workflow for confidential risk screenings; mail out sample caregiver letter that describes time alone | Clinical champion/nurse manager develop workflow; quality improvement lead send out caregiver letter; health informatics lead pull data on time alone offered and provided | 2/5/2023 | Percent of visits with adolescent patients that time alone with clinician was offered and provided | Monthly | 70% of unduplicated adolescent patients will be offered and provided time alone over next 12 months
#N/A
#N/A
#N/A

## 8. Trauma-Informed
Improvement Goal: Trauma-Informed Approach Integrated Into Care
Instructions: Complete the following action plan using the results from your needs assessment. Your team can use this action plan regularly to keep track of tasks and assess your progress. Column A/B: Insert your change strategy(ies) from the drop-down menu and Column B will automatically populate the associated focus area Column C: List the tools and resources that you want to use for your chosen change strategy(ies) Column D: Develop action items/tasks for your team to complete Column E: Identify who will be responsible for completing each action item/task Column F: List the date that the action item/task will be completed Column G: List how you will measure the impact of your project (e.g., what performance measures are used) Column H: List the frequency you will review progress Column I: List the target goal (e.g., percentage or number increase) Column J: Add any additional reflections/notes here
Change Strategy | Focus Area (auto-populated) | Tools/Resources | Action items/tasks to complete | Person(s) responsible | Date action item/task will be completed | How will you measure the impact of this? (e.g., what performance measure used) | How frequently will you review progress? | What is your goal? (e.g. percentage increase you are hoping to see) | Additional Reflections/Notes
Example:
Train staff to be aware of trauma and adverse childhood experiences and in using a trauma-informed approach | Equipping teams | Journey from Trauma-Aware to Trauma Informed Meeting Package | Identify meeting time for care team; print out checklist/discussion questions in advance; Identify facilitator with expertise in trauma | Administrative lead | 2/5/2023 | Percent of staff trained in using a trauma-informed approach | Monthly | 100% of care team members trained in using a trauma-informed approach in 6 months
#N/A
#N/A
#N/A

## Improvement Team & Timeline
Q4T (Quality for Teens) Improvement Team
Your improvement team will lead the improvement efforts at your health center. Read below for a description of some example team responsibilities, then complete the table. In the table, list all of the implementation team members who will participate from your health center.
Improvement Team
It is important to have a cross-functional team of 3-5 members to participate in your quality improvement efforts. To facilitate system-wide change, consider including care-team members from all organizational levels as part of the improvement team, including administrators, clinicians, and staff from the front desk/ call-center as well as health informatics, finance, and QI departments. The table below provides some ideas for different roles that your team may want to include. Adjust the team role column as needed for your unique health care setting.
Team Champion
It is important to designate a team champion. This person should be skilled in supporting the progress of a quality improvement initiative such as this. Designate in the table below which of the team members will be the champion.
Team Role | Name | Team Champion
Clinician (MD or APP) Lead
Quality Improvement Lead
Clinic/Nurse Manager Team Member
Senior Administrator Team Member
Revenue and Billing Representative
Health Informatics Specialist
Behavioral Health Team Member
Other
Q4T (Quality for Teens) Improvement - Key Questions to Create Your Timeline
Estimated months to complete QI initiative?
Frequency of team meetings?
Meeting dates scheduled in advance? Write down dates or recurring time.
Frequency of engaging senior leaders?

## Reference (hidden)
Improvement Goals | Change Stategies | Focus Area
Recommended Screening for Sexual Activity and Sexual Risk Assessment Conducted | Establish a policy to screen every adolescent patient for sexual activity and conduct sexual risk assessment at least annually | Key Foundation
Recommended Screening for Sexual Activity and Sexual Risk Assessment Conducted | Train the care team on conducting sexual histories and sexual risk assessments | Equipping Teams
Recommended Screening for Sexual Activity and Sexual Risk Assessment Conducted | Implement a clinic workflow to conduct a risk assessment using a tool that includes sexual risk | Service Delivery
Recommended Screening for Sexual Activity and Sexual Risk Assessment Conducted | Use electronic health records (ERHs) to support sexual history taking and risk assessment | Service Delivery
Recommended Screening for Sexual Activity and Sexual Risk Assessment Conducted | Educate parents about the importance of sexual risk assessment | Engaging Adolescent Patients and Families
BEHAVIORAL COUNSELING RELATED TO SEXUAL HEALTH CONDUCTED | Establish a policy to provide behavioral counseling for all sexually active adolescents to prevent sexually transmitted infections (STIs) | Key Foundation
BEHAVIORAL COUNSELING RELATED TO SEXUAL HEALTH CONDUCTED | Train the care team to provide behavioral counseling about risk and protective behaviors | Equipping Teams
BEHAVIORAL COUNSELING RELATED TO SEXUAL HEALTH CONDUCTED | Implement a clinic workflow to provide counseling about risk and protective behaviors for sexual health | Service Delivery
BEHAVIORAL COUNSELING RELATED TO SEXUAL HEALTH CONDUCTED | Equip parents to have conversations with their adolescents that reinforce behavioral counseling messages | Engaging Adolescent Patients and Families
ROUTINE CHLAMYDIA AND GONORRHEA SCREENING | Establish a policy to include recommended chlamydia and gonorrhea screening as part of preventive care | Key Foundation
ROUTINE CHLAMYDIA AND GONORRHEA SCREENING | Train the clinical care team on recommended chlamydia and gonorrhea screening for sexually active adolescents and tracking, following up, and treating those who have positive screens | Equipping Teams
ROUTINE CHLAMYDIA AND GONORRHEA SCREENING | Implement a clinic workflow to conduct recommended chlamydia and gonorrhea screening | Service Delivery
ROUTINE CHLAMYDIA AND GONORRHEA SCREENING | Standardize coding and billing practice for chlamydia and gonorrhea screening and treatment | Service Delivery
ROUTINE CHLAMYDIA AND GONORRHEA SCREENING | Inform patients and caregivers of clinical recommendations and health center protocols regarding chlamydia and gonorrhea screening | Engaging Adolescent Patients and Families
PATIENT-CENTERED CONTRACEPTIVE COUNSELING PROVIDED | Establish a policy to provide adolescents with patient-centered contraceptive counseling | Key Foundation
PATIENT-CENTERED CONTRACEPTIVE COUNSELING PROVIDED | Train the care team in shared-decision making and communication skills to deliver patient-centered contraceptive counseling | Equipping Teams
PATIENT-CENTERED CONTRACEPTIVE COUNSELING PROVIDED | Implement a patient-centered contraceptive counseling framework | Service Delivery | `
PATIENT-CENTERED CONTRACEPTIVE COUNSELING PROVIDED | Equip parents with information about contraceptive methods | Engaging Adolescent Patients and Families
SAME-DAY ACCESS TO FULL RANGE OF CONTRACEPTIVE METHODS | Establish policies that support adolescent access to the full range of contraceptive services | Key Foundation
SAME-DAY ACCESS TO FULL RANGE OF CONTRACEPTIVE METHODS | Ensure care team members are comfortable and trained in provision and management of all methods of contraception | Equipping Teams
SAME-DAY ACCESS TO FULL RANGE OF CONTRACEPTIVE METHODS | Train and mentor care team members in LARC insertion, management, and removal | Equipping Teams
SAME-DAY ACCESS TO FULL RANGE OF CONTRACEPTIVE METHODS | Implement a clinic workflow to ensure same-day contraceptive access is available every day of clinical services | Service Delivery
SAME-DAY ACCESS TO FULL RANGE OF CONTRACEPTIVE METHODS | Optimize reimbursement for contraceptive services, including LARC devices | Service Delivery
WELCOMING AND AFFIRMING ENVIRONMENT FOR ADOLESCENT PATIENTS | Establish policies that support adolescent access to services | Key Foundation
WELCOMING AND AFFIRMING ENVIRONMENT FOR ADOLESCENT PATIENTS | Create youth-friendly spaces | Key Foundation
WELCOMING AND AFFIRMING ENVIRONMENT FOR ADOLESCENT PATIENTS | Ensure common understanding of adolescent development | Equipping Teams
WELCOMING AND AFFIRMING ENVIRONMENT FOR ADOLESCENT PATIENTS | Train staff to provide respectful, inclusive, youth-friendly care | Equipping Teams
WELCOMING AND AFFIRMING ENVIRONMENT FOR ADOLESCENT PATIENTS | Document sexual orientation and gender identity for all patients | Service Delivery
WELCOMING AND AFFIRMING ENVIRONMENT FOR ADOLESCENT PATIENTS | Engage youth to both assess and help create youth-friendly spaces | Engaging Adolescent Patients and Families
CONFIDENTIALITY PROTECTED | Establish policies that support adolescent access to confidential services | Key Foundation
CONFIDENTIALITY PROTECTED | Implement a clinic workflow to provide time alone at every patient visit | Service Delivery
CONFIDENTIALITY PROTECTED | Ensure confidentiality of the patient’s medical record | Service Delivery
CONFIDENTIALITY PROTECTED | Ensure coding and billing practices protect confidentiality | Service Delivery
CONFIDENTIALITY PROTECTED | Communicate the health center’s time alone and confidentiality practices and minors’ rights | Engaging Adolescent Patients and Families
USE A TRAUMA-INFORMED APPROACH | Assess organizational needs related to integrating a trauma-informed approach | Key Foundation
USE A TRAUMA-INFORMED APPROACH | Train staff to be aware of trauma and adverse childhood experiences and in using a trauma-informed approach | Equipping Teams