## Center Education
Center Engagement & Education Plan
| Start Date | Frequency | Completion | Owner | Resources | Notes
Steering Committee
Kick- Off Meeting | 2 mos prior |  |  | CMO / CM Leader
CM Project updates | 2 mos prior | Weekly |  | CM Leader
Monthly Meeting |  |  | Ongoing | CM Leader |  | In Person or Virtual
Center Managers/ Supervisors
Manager Meeting - Monthly | 6 wks prior | Monthly | Ongoing | CM Leader |  | Include Role specific resources for managers to use
Email communications |  | weekly x 4 2 wks prior and 4 wks after go live
What staff will see that is different - by role. Wkly x 2 |  |  |  | CM Leader
Aligning Measures of Success - ongoing Review | 2 wks prior | Monthly
Providers - MD/DO/NP/PA
Grand Rounds | 6 wks prior | Monthly x 6 |  |  | PP | CM Overview; Pilot Update : EHR- what is different;
Email & Printed communication | 2 wks prior | weekly x 4
Message includes CM Goals - Measures of Success | [5 empty] | Align with Center goals/quality measures
Center Communication |  |  |  | Center Manager
Pilot updates via Managers to each role |  |  |  | Center Manager |  | Role specific communication
Communication re: transition of tasks - What does this look |  |  |  | Center Manager
Center meetings | 4 wks prior | Monthly |  | CM Leader / Center Manager
Posters for Center breakrooms - communal space
PATIENTS
Slow roll out
Examples of communication for team to use for patients referred to CM |  |  |  | CM Leader
Brochure for patients who are referred to CM | Go Live |  |  | CM Leader
All Patient Communication - Posters; Portal Message, etc. | 3-6 mos after Go Live